IGO-INGO Working Group Work Plan & Timeline (updated 21 August 2013)

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 14 August | IGO-INGO WG Meeting | Review Recommendations Matrix for eventual Consensus Call | Working Group |
| 21 August | IGO-INGO WG Meeting | Review Recommendations Matrix for eventual Consensus Call | Working Group |
| 28 August | IGO-INGO WG Meeting | Update Final Report / Consensus Call | Staff / Working Group |
| 03 September | IGO-INGO WG Meeting | Consensus Call Response & Minority Position Statements due | Working Group |
| 04 September | IGO-INGO WG Meeting | Update Final Report | Staff / Working Group |
| 05 September | Initiate Public Comment on Final Report | Public comment form | ICANN Staff |
| 05 September | GNSO Council Meeting | None | GNSO Council |
| 11 September | IGO-INGO WG Meeting | As required | Working Group |
| 18 September | IGO-INGO WG Meeting | As required | Working Group |
| 25 September | IGO-INGO WG Meeting | As required | Working Group |
| 26 September | Comment closes, Reply period begins | None | ICANN Staff |
| 30 September | Motions & documents due for GNSO Council Meeting10 October | None | None |
| 02 October | IGO-INGO WG Meeting | As required | Working Group |
| 09 October | IGO-INGO WG Meeting | Review Comments / Prepare Final Report | Working Group |
| 10 October | GNSO Council Meeting | Brief Council on IGO-INGO Recommendations | GNSO Council |
| 16 October | IGO-INGO WG Meeting | Review Comments / Prepare Final Report & Motion for delivery to the GNSO Council | Working Group |
| 17 October | Reply period closes | None | ICANN Staff |
| 21 October | Motions & documents due for GNSO Council Meeting10 October | None | None |
| 23 October | IGO-INGO WG Meeting | As required | Working Group |
| 31 October | GNSO Council Meeting | Council to consider and vote on IGO-INGO Recommendations | GNSO Council |
| 10 November | Motions & documents due for GNSO Council Meeting10 October | None | None |
| 20 November | GNSO Council Meeting – Buenos Aires | None | GNSO Council |
| Archive |  |  |  |
| Target Date | What | Deliverable / Topic for Discussion | Who |
| 31 October | Develop Charter | Statements of Interest; Review 1st draft of charter created by Staff | Working Group |
| 07 November | Develop Charter; Election of WG Chair(s); Deadline to submit documents to Council | Finalize charter as agreed by the team; Determine WG Chairs | Working Group |
| 14 November | IGO WG Meeting | Statements of Interest; review work plan; begin review of WG Charter Issues | Working Group |
| 15 November | GNSO Council Meeting | Council to approve IGO-INGO Charter; Review deliberation of IOC/RCRC DT recommendations & communication to GAC | GNSO Council |
| blank |  |  |  |
| 21 November | IGO WG Meeting | Cancelled | None |
| 22 November | US Holiday | None | None |
| 28 November | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 05 December | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 12 December | IGO-INGO WG Meeting | Work Package Analysis | Working Group |
| 19 December | IGO-INGO WG Meeting | Review interim results of Work Package; create initial draft of progress report | Working Group |
| 20 December | GNSO Council Meeting | None | GNSO Council |
| 24 December | Holiday | None | None |
| 26 December | Holiday / IGO-INGO WG Meeting Cancelled | None | None |
| 02 January 2013 | IGO-INGO WG Meeting - Cancelled | Cancelled | Working Group |
| 09 January | IGO WG Meeting; Documents & motions due for 17 JAN 2013 GNSO Council meeting | Review interim results of Work Package / Finalize progress report | Working Group |
| Target Date | What | Deliverable / Topic for Discussion | Who |
| 16 January | IGO-INGO WG Meeting | Review interim results of Work Package / Review interim Protections Report | Working Group |
| 17 January | GNSO Council Meeting | Present Preliminary Findings | GNSO Council; IGO-INGO WG Chair |
| 23 January | IGO-INGO WG Meeting | Review results of Work Package / Formulate initial recommendations | Working Group |
| 30 January | IGO-INGO WG Meeting | Review results of Work Package / Formulate initial recommendations | Working Group |
| 31 January | Deadline for ICANN Board resolution on 2nd level Protections of IOC/RCRC | GNSO Council submits response to ICANN Board & GAC | GNSO Council |
| 06 February | IGO-INGO WG Meeting | TBD | Working Group |
| 13 February | IGO-INGO WG Meeting | TBD | Working Group |
| 14 February | GNSO Council Meeting | None | GNSO Council |
| 20 February | IGO-INGO WG Meeting | Review Protections Matrix, Qualification Criteria | Working Group |
| 27 February | IGO-INGO WG Meeting | Review Protections Matrix, Qualification Criteria | Working Group |
| 28 February | Deadline for ICANN Board resolution on 2nd level Protections of certain IGO Names | None | None |
| 06 March | IGO-INGO WG Meeting | Review possible recommendations & Proposals | Working Group |
| 06 March | Documents & motions due for 14 MAR 2013 GNSO Council meeting |  | None |
| 13 March | IGO-INGO WG Meeting | Review GC Response, Continue Qualification Criteria | Working Group |
| 14 March | GNSO Council Meeting | None | GNSO Council |
| 20 March | IGO-INGO WG Meeting | Continue Qualification Criteria; Protections; Recommendations/Rationale | Working Group |
| 27 March | IGO-INGO WG Meeting | Review and Revise Initial Report & Recommendations | Working Group |
| 01 April | Initiate Public Comment on Initial Report | Public comment form | ICANN Staff |
| 02 April | Documents & motions due for 10 APR 2013 GNSO Council meeting | None | None |
| 10 April | GNSO Council Meeting – Beijing | None | GNSO Council |
| 30 April | Public Comment Period closes, reply period begins | None | ICANN Staff |
| 1 May | IGO-INGO WG Meeting | Begin Review of Public Comments | Working Group |
| 8 May | IGO-INGO WG Meeting | Continue Review of Public Comments | Working Group |
| 15 May | IGO-INGO WG Meeting | Complete Final Report | Working Group |
| 17 April | IGO-INGO WG Meeting | Continue Protections discussions | Working Group |
| 24 April | IGO-INGO WG Meeting | Review and Revise Initial Report & Recommendations | Working Group |
| 1 May | IGO-INGO WG Meeting | Review and Revise Initial Report & Recommendations | Working Group |
| 15 May | IGO-INGO WG Meeting | Discuss possible recommendations for report | Working Group |
| 16 May | GNSO Council Meeting | None | GNSO Council |
| 22 May | IGO-INGO WG Meeting - CANCELLED | WG to review Report via list | None |
| 22 May | Deliver 2nd Draft of Initial Report to WG |  | None |
| 29 May | IGO-INGO WG Meeting | Review Final Draft of Initial Report | Working Group |
| 30 May | Initiate Public Comment on Initial Report | Public comment form | ICANN Staff |
| 05 June | IGO-INGO WG Meeting | Continue Deliberations | Working Group |
| 12 June | IGO-INGO WG Meeting | Continue Deliberations | Working Group |
| 19 June | IGO-INGO WG Meeting | Review of Public Comments | Working Group |
| 20 June | Public Comment Period closes, reply period begins | None | ICANN Staff |
| 26 June | IGO-INGO WG Meeting | Continue Review of Public Comments / Review Final Report Draft | Working Group |
| 3 July | IGO-INGO WG Meeting | Review Final Report Draft | Working Group |
| 11 July | Reply period closes | None | ICANN Staff |
| 19 July | Durban Session on IGO | Present Recommendations via WG Face to Face and present to GNSO Council | Working Group |