Draft IGO-INGO Working Group Work Plan & Timeline (updated 7 November 2012)

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 31 October | Develop Charter | Statements of Interest; Review 1st draft of charter created by Staff | Working Group |
| 07 November | Develop Charter; Election of WG Chair(s); Deadline to submit documents to Council | Finalize charter as agreed by the team; Determine WG Chairs | Working Group |
| 14 November | IGO WG Meeting | Statements of Interest; review work plan; create sub-groups A & B | Working Group |
| 15 November | GNSO Council Meeting | Council to approve IGO-INGO Charter; Review deliberation of IOC/RCRC DT recommendations & communication to GAC | GNSO Council |
| 19 November | IGO WG Meeting | Review WG Charter requirements & refine work plan | Working Group |
| 21 November | IGO WG Meeting | Review Comments from SGs & Cs | Working Group |
| 22 November | US Holiday | None | None |
| 28 November | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 05 December | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 12 December | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 12 December | GNSO Council Meeting | None | GNSO Council |
| 19 December | IGO WG Meeting | Create sub-group A recommendation report; Confirm 2013 work plan | Working Group |
| 24 December | Holiday | None | None |
| 02 January 2013 | IGO WG Meeting | Finalize sub-group A recommendation report and ready for submission to GNSO Council ; Create Communication to ICANN Board for 31JAN2013 Deadline | Working Group |
| 09 January | IGO WG Meeting; Documents & motions due for 15 Jan GNSO Council meeting | Finalize sub-group A recommendation report and ready for submission to GNSO Council | Working Group |
| 16 January | IGO WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 17 January** | GNSO Council Meeting | None | GNSO Council |
| 23 January | IGO WG Meeting | Create Initial Report | Working Group |
| 30 January | IGO WG Meeting | Revise Initial Report | Working Group |
| 31 January | Deadline for ICANN Board resolution on 2nd level Protections of IOC/RCRC | None | None |
| 06 February | Public Comment Period Opens | Finalize and Post Initial report and open public comment period | Working Group / Staff |
| 21 February** | GNSO Council Meeting | None | GNSO Council |
| 10 March | Public Comment Period Closes | None / Create Public Comment Review Tool | Staff |
| 13 March | IGO WG Meeting | Review Public Comments | Working Group |
| 20 March | IGO WG Meeting | Review Public Comments / Create Final Report | Working Group |
| 21 March** | GNSO Council Meeting | None | GNSO Council |
| 27 March | IGO WG Meeting | Review Public Comments / Revise Final Report | Working Group |
| 03 April | IGO WG Meeting | Review Public Comments / Revise Final Report | Working Group |
| 10 April | Reply Comment Period Closes | Finalize Public Comment Review Tool | Staff |
| 10 April | IGO WG Meeting | Complete Public Comments review, Complete Final Report & submit to GNSO Council | Working Group |
| 18 April** | GNSO Council Meeting | None | GNSO Council |

** Dates subject to change pending 2013 GNSO Council schedule