**Draft Work Plan for IRTP Part D PDP Working Group to submit Final Report for ICANN 50 in London**

|  |  |  |  |
| --- | --- | --- | --- |
| **Target Date** | **What** | **Deliverable/Topic for Discussion** | **Who** |
| 07 April | WG Meeting | Finalise Use Cases | All |
| 14 April | WG Meeting | Finalise Use Cases | All |
| 21 April | WG Meeting | Finalise Use Cases / Start reviewing Comments | All |
| 25 April | Reply Period Closes | Close Reply Period | Staff |
| 28 April | WG Meeting | Review comments/replies | All |
| 5 May | WG Meeting | Review comments/replies | All |
| 12 May | WG Meeting | Review comments/replies | All |
| 19 May | WG Meeting | Review comments/replies | All |
| 26 May | WG Meeting | Review Final Review | All |
| 02 June | WG Meeting | Review Final Review and Consensus Call | All |
| 02 June | Publication Deadline for London | As the Final Report does not have to go out for Public Comment, this is an optional deadline | Staff |
| 09 June | Reserve meeting | Additional meeting if need be. | All |
| 15 June | Motion Deadling for London | Submit Motion to pass the Final Report to the GNSO Council | Staff/Co-Chairs |