Draft UDRP-Lock Working Group Work Plan & Timeline (updated 30 August 2012)

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 16 April | UDRP-Lock WG Meeting ; First Call of WG | Statements of Interest | Working Group |
| 26 April | UDRP-Lock WG Meeting ; Election of WG Chairs | Determine WG Chairs; Statements of Interest; Review Charter | Working Group |
| 3 May | UDRP-Lock WG Meeting | Open public comment forum | Working Group |
| 10 May | UDRP-Lock WG Meeting | Open public comment forum; outreach; develop work plan | Working Group |
| 17 May | UDRP-Lock WG Meeting | Develop outreach survey to Registrars and UDRP Providers | Working Group |
| 24 May | UDRP-Lock WG Meeting | Develop outreach survey to Registrars and UDRP Providers; Plan for Prague | Working Group |
| 31 May | UDRP-Lock WG Meeting | Develop outreach survey to Registrars and UDRP Providers; Plan for Prague | Working Group |
| 7 June | UDRP-Lock WG Meeting | Develop outreach survey to Registrars and UDRP Providers; Plan for Prague | Working Group |
| 28 June | UDRP-Lock Face to Face session in Prague | Review of WG Status and community discussion | Working Group |
| 12 July | UDRP-Lock WG Meeting | Recap F2F in Prague; Review Survey Responses | Working Group |
| 19 July | UDRP-Lock WG Meeting | Review Survey Responses | Working Group |
| 2 August | UDRP-Lock WG Meeting | Review Survey Responses | Working Group |
| 16 August | UDRP-Lock WG Meeting | Review WG Charter requirements & next steps | Working Group |
| 30 August | UDRP-Lock WG Meeting | Review WG Charter requirements & work plan | Working Group |
| 3 September | Initial Public Comment Period Closes and Reply period opens | None | None |
| 6 September | UDRP-Lock WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 13 September | UDRP-Lock WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 20 September | UDRP-Lock WG Meeting | Respond to Charter Questions / Formulate Recommendations | Working Group |
| 24 September | Reply Comment Period Closes | Create Public Comment Review Tool | Staff |
| 27 September | UDRP-Lock WG Meeting | Review Public Comments / Create Initial Report | Working Group |
| 4 October | UDRP-Lock WG Meeting | Review Public Comments / Create Initial Report | Working Group |
| 15 October | UDRP-Lock Face to Face session in ICANN 45 - Toronto | Public review of initial recommendations | Working Group |
| 25 October | UDRP-Lock WG Meeting | Create Initial Report | Working Group |
| 1 November | UDRP-Lock WG Meeting | Revise Initial Report | Working Group |
| 8 November | UDRP-Lock WG Meeting | Revise Initial Report | Staff |
| 15 November | UDRP-Lock WG Meeting | Revise Initial Report | Working Group |
| 22 November | US Holiday |  |  |
| 29 November | UDRP-Lock WG Meeting | Post Initial report and open public comment period | Staff |
| 6 December | UDRP-Lock WG Meeting | Meeting if required / Create 2013 Work Plan | Chairs / Staff |
| 13 December | UDRP-Lock WG Meeting | Meeting if required | Working Group |