# ICANN GNSO Operating Steering Committee (OSC)

# Chairman’s Overview of Work Items v4:  April 2010

Wiki:	  https://st.icann.org/icann-osc/index.cgi?operations_steering_committee_osc

Timeline: all teams to complete all work by 1 June 2010

| Deliverable | Item | Status (team) | Status (OSC) | Complete? |
| --- | --- | --- | --- | --- |
| GNSO Council Operations Team GCOT Chair: Ray Fassett |
| Section A: Tasks SENT to the OSC |
| GNSO Operating Procedures (GOP) | Chapter 5: Statements of Interest | Completed; awaiting OSC feedback | OSC edits added. OSC final review ends 11.4.10 Sending to Council 12.4.10 |  |
| Section B: Tasks in Progress to be SENT latest 1 June 2010 |
| GOP | Section 2.1: Term Limits | To be delivered to OSC by 9 April |  |  |
| GOP | Section 2.4: Board Seat Elections | Staff draft of 7 April under review. Targeted to be sent to OSC by 1 May |  |  |
| GOP | Section 3.8: Vacancies and Absences | Changes under review. Targeted to be sent to OSC by 1 June |  |  |
| GOP | Chapter 4: Section 4.1: Quorum Section 4.2: Voting Thresholds Section 4.3: Motions and Votes Section 4.4: Absentee Voting Section 4.5: Abstentions | Sent to OSC in Nairobi. Changes being made due OSC feedback. Targeted to be sent to OSC by 1 June. |  |  |
| Exec Summary & Abstentions Analysis-2009 | Companions to Chapter 4-Voting | Sent to OSC on 6 March. Resend to OSC after Chapter 4 is ready for resubmission? |  |  |
| Section C: GOP Sections NOT recommended for amendment |
| GOP | Section 1 Intro & Scope |  |  | No action |
| GOP | Sections 2.2, 2.3 |  |  | No action |
| GOP | Sections 3.1-3.7 |  |  | No action |
| Section D: GOP Sections under auspices of PSC or staff |
| GOP | Table of Contents | Ken will add TOC on completion |  | No action |
| GOP | Chapter 6: GNSO Work Prioritization | Work Prioritization Model Drafting Team (WPM-DT) |  | No action |
| GOP | Chapter 7: Working Group Guidelines | Working Group Work Team (WGT) |  | No action |
| GOP | Chapter 8: PDP | PDP Work Team (PDPT) |  | No action |
|  | Section 9 Document Revisions | Ken will add a table to document revisions |  | No action |
| Constituency Stakeholder Group CSG Chair: Olga Cavalli |
| Task 1 Recommen-dations to enhance Constituencies and Stakeholder Groups | Subtask 1: Develop recommendations for a set of participation rules and operating procedures, which all constituencies should abide by | Done Will be sent to OSC with Subtasks 2 and 3 |  |  |
|  | Subtask 2: Develop recommendations for clear operating principles for each constituency to ensure that all constituencies function in a representative, open, transparent and democratic manner | Finalizing Will be sent to OSC with Subtasks 1 and 3 |  |  |
|  | Subtask 3: Develop recommendations for creating and maintaining a database of all constituency members and others not formally a part of any constituency that is up-to-date and publicly accessible | Finalizing Will be sent to OSC with Subtasks 1 and 2 |  |  |
|  | Subtask 4 Tool Kit of Services | Done | Council 5 Nov 09 | Done (Approved by Council 17 Dec 2009. Shared with Board. Staff to implement.) |
| Task 2 Develop a global outreach program to broaden participation in current constituencies |  | Work not yet started |  |  |
| Communication & Coordination Team CCT Chair: Mason Cole |
| Recommendations | Report 1 Technology | OSC review completed | JH to integrate both reports 6.4.10 |  |
| Recommendations | Report 2 Communications & Coordination | OSC review completed. | JH to integrate both reports 6.4.10 |  |

Key: Completed tasks or not OSC volunteer related

Key: OSC action required