Policy & Implementation WG – Updated Work Plan

Updated 29 September 2014

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 15 October | Open WG Meeting | Provide brief overview of WG deliberations to date and possible recommendations in relation to charter question 2 Review work plan Review implementation process graphic and confirm which issues the WG needs to address in order to answer charter question 3, 4 and 5 | WG |
| 29 October | WG Meeting | Review input received during F2F meeting in LA Confirm work plan Commence deliberations on issues identified to address charter questions 3, 4 and 5 | WG |
| 29 October | Share draft manuals | Share draft manuals for GNSO Guidance Process, GNSO Input Process and GNSO Fast-Track PDP Process for review by the WG | Staff |
| 5 November | WG Meeting | Continue deliberations on issues identified to address charter questions 3,4 and 5 |  |
| 11 November | WG Deadline for comments on draft manuals | Deadline for WG to provide input / comments / questions on draft manuals | WG |
| 12 November | WG Meeting | Review and discuss comments received on draft manuals | WG |
| 19 November | WG Meeting | Continue review and discussion of comments received on draft manuals Continue deliberations on issues identified to address charter questions 3,4 and 5 | WG |
| 26 November | WG Meeting | Continue review and discussion of comments received on draft manuals Continue deliberations on issues identified to address charter questions 3,4 and 5 | WG |
| 3 December | WG Meeting | Continue deliberations on issues identified to address charter questions 3,4 and 5 | WG |
| 11 December | WG Meeting | Continue deliberations on issues identified to address charter questions 3,4 and 5 | WG |
| 17 December | WG Meeting | Review draft recommendations resulting from deliberations on issues identified to address charter questions 3, 4 and 5 | WG |
| 22 December | Draft Initial Report circulated | Share first draft of Initial Report which incorporates the materials prepared by the WG as well as proposed recommendations for community input | Staff |
| 7 January | WG Meeting | Review and discuss comments / edits / input received on draft Initial Report | WG |
| 12 January | WG | Deadline for comments / edits / input on draft Initial Report | WG |
| 14 January | WG Meeting | Continue review and discuss comments / edits / input received on draft Initial Report | WG |
| 19 January | Publication Deadline | Publication deadline for documents for discussion at ICANN 52 |  |
| 19 January | Posting of Initial Report | Posting of Initial Report for public comment | Staff |
| 11 February | Open WG Meeting / Workshop | Presentation of Initial Report and request for input during ICANN 52 | WG |
| 13 March | Closing of public comment forum |  | Staff |
| 18 March | WG Meeting | Commence review of comments received [Note, WG meetings may already commence before this date if deemed appropriate / necessary by WG Chairs to start deliberations on outstanding items or review of input already received) | WG |
| 25 March | WG Meeting | Continue review of public comments | WG |
| 1 April | WG Meeting | Continue review of public comments | WG |
| 8 April | WG Meeting | Continue review of public comments | WG |
| 13 April | Draft Final Report circulated to WG | Share first draft of Final Report which addresses public comments as discussed by WG and possible other updates | Staff |
| 15 April | WG Meeting | Review Final Report | WG |
| 22 April | WG Meeting | Continue review of Final Report | WG |
| 29 April | WG Meeting | Continue review of Final Report | WG |
| 4 May | Submit Final Report | Submit Final Report to GNSO Council |  |