Estimated Timelines for new processes recommended by Policy & Implementation Working Group (in days)

Assumptions:

- The issues that are subject to an EPDP and GGP are narrowly scoped and often more limited than subjects under consideration in a PDP.

- In the case of a GIP, most of the times, no public comment period will be required as it is expected to mostly concern input in response to an open public comment period or specific request from an entity other than the Board.

- As with a PDP, the actual duration of each phase will depend on a number of factors such as complexity of the issue, resources available to undertake the work (both community and staff) as well as general support (or lack thereof) for possible recommendations. These are just estimates.

|  | PDP (Median) | EPDP Steps | EPDP (Estimate) | GIP Steps | GIP (Estimate) | GGP Steps | GGP (Estimate) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Request for an Issues Report | 0 |  |  |  |  |  |  |
| Preliminary Issue Report | 54 |  |  |  |  |  |  |
| Submission of Final Issue Report | 52,5 |  |  |  |  |  |  |
| Initiation of PDP | 130,5 | Initiation of EPDP | 0 | Initiation of GIP | 0 | Initiation of GGP | 0 |
| Approval of WG Charter | 157 | Approval of WG Charter | 0 |  |  |  |  |
| Publication Initial Report | 408 | Publication of Initial Report | 150 |  |  | Publication of Initial Guidance Report | 150 |
| Publication Final Report | 578 | Publication of Final Report | 235 | Submission of GNSO Input | 60 | Publication of Final Report | 235 |
| Council Vote | 588 | Council Vote | 245 | GNSO Approval / non-objection | 70 | Council Vote | 245 |
| Board Vote | 849 | Board Vote | 380 | Submission | 80 | Board Vote | 380 |
| Implementation Effective Date | 1143 | Implementation Effective Date | 527 |  |  | Implementation | 527 |

|  | IRTP Denials | IRTP Part A | Fast Flux | Domain Tasting | IRTP Part B | PEDNR | IRTP Part C | UDRP Lock | Thick Whois | IGO/INGO | IRTP Part D | Curative Rights | Median |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Request for an Issues Report | 0 (20 Sep07) | 0 (8 May08) | 0 (6 March08) | 0 (9 May07) | 0 (16 April09) | 0 (20 Nov08) | 0 (22 Jun11) | 0 (3 Feb11) | 0 (22 Sept11) | 0 (12 Apr12) | 0 (17 Oct12) | 0 (20 Nov13) |  |
| Preliminary Issue Report |  |  |  |  |  |  | 34 (25 Jul11) | 114 (27 May11) | 61 (21 Nov11) | 54 (4 Jun12) | 27 (12 Nov12) | 111 (10 March14) | 54 |
| Submission of Final Issue Report | 29 (19 Oct07) | 15 (23 May08) | 19 (25 March08) | 36 (14 June07) | 29 (15 May09) | 15 (5 Dec08) | 69 (29 Aug11) | 243 (3 Oct11) | 134 (2 Feb12) | 173 (1 Oct12) | 84 (8 Jan13) | 198 (5 June14) | 52,5 |
| Initiation of PDP | 61 (20 Nov07) | 48 (25 June08) | 63 (8 May08) | 175 (31 Oct07) | 69 (24 June09) | 168 (7 May09) | 93 (22 Sept11) | 316 (15 Dec11) | 175 (14 Mar12) | 189 (17 Oct12) | 93 (17 Jan13) | 218 (25 June14) | 130,5 |
| Approval of WG Charter |  | 70 (17 July08) | 84 (29 May08) |  | 98 (23 July09) | 216 (24 June09) | 93 (22 Sept11) | 406 (14 Mar12) | 383 (8 Oct12) | 218 (15 Nov12) | 93 (17 Jan13) | 218 (25 June14) | 157 |
| Publication Initial Report | 179 (17 March08) | 245 (8 Jan09) | 326 (26 Jan09) | 243 (7 Jan08) | 408 (29 May10) | 557 (31 May10) | 346 (1 Jun12) | 772 (15 Mar13) | 639 (21 Jun13) | 429 (14 Jun13) | 503 (3 Mar14) |  | 408 |
| Publication Final Report | 202 (9 April08) | 315 (19 March09) | 518 (6 August09) | 332 (4 April08) | 775 (30 May 2011) | 937 (14June11) | 476 (9 Oct 12) | 884 (5 July13) | 761 (21 Oct13) | 578 (10 Nov13) | 709 (25 Sept14) |  | 578 |
| Council Vote | 392 (16 Oct08) | 343 (16 April09) | 546 (3 Sept09) | 345 (17 April08) | 798 (22 June 2011) | 1005 (21 July 2011) | 484 (17 Oct 12) | 911 (1 Aug13) | 771 (31 Oct13) | 588 (20 Nov13) | 729 (15 Oct14) |  | 588 |
| Board Vote | 415 (7 Nov08) | No board vote | No board vote | 415 (26 June08) | 862 (25 Aug11) | 1073 (28 Oct11) | 548 (20 Dec12) | 969 (28 Sept13) | 870 (7 Feb 2014) | 749 (30 Apr14) | 849 (12 Feb15) |  | 849 |
| Implementation Effective Date | 543 (15 Mar09) | N/A | N/A | 694 (1 Apr09) | 1143 1 June 2012 | 1746 (31 Aug 2013) |  | 1640 (31 July15) |  |  |  |  | 1143 |

Actual PDP Timelines

# Footnotes

See table on next page from which this information is derived

Assuming that per current practice the charter could be approved at the same time as the initiation

This assumes no public comment period.

Required per the revised GNSO PDP approved in December 2011

Target date

Followed by launch of drafting team on 17 April 2008, which produced its final report on 4 June 2008, whose recommendations where adopted by the GNSO Council in October 2008.

Part of the recommendations were considered by the ICANN Board on that date

Part of the recommendations were implemented by this date