Draft Policy & Implementation Working Group Work Plan & Timeline (Proposed )

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 16 Oct 13 | Status and Discussion of PIWG Working Plan Sub-team | Draft Sub-Team Mind Map and Proposed Working Plan Grid | PIWG Work Plan Sub-team |
|  | Discuss PIWG Work Plan Sub-team Status | Revisions to Drafts | PI Working Group |
| 23 Oct 13 | Submission of Revised PIWG Work Plan Sub-team Mind Map and Draft Working Plan Grid to PIWG | Revised Draft Mind Map and Draft Working Plan Grid | PIWG Work Plan Sub-team |
| 28 Oct 13 | Finalize Materials for BA Discussion | List of proposed Terms for Definition; List of resources, articles, and references for study; draft directed questions for community participation | PIWG Work Plan Sub-team |
| 30 Oct 13 | Preliminary Discussion of Work Plan Mind Map and Grid; and List of proposed Terms for Definition and Materials for Review. Possible Discussion of Resources and Questions regarding Principals Underlying Policy and Implementation Process to Distribute to GNSO Council at BA Meeting | Revised list of proposed Terms for Definition and comments on PIWG Work Plan Sub-team materials; | PI Working Group |
| 4 November 13 | Draft Working Plan for review by PI Working Group | Revised Draft Work Plan and Timeline, and PIWG Work Plan Sub-team Mind Map and Grid for BA Discussion | PIWG Work Plan Sub-team |
| 13 November | PI Working Group Telemeeting; Develop Questions regarding Principals Underlying Policy and Implementation Process to Distribute to GNSO Council at BA Meeting |  | PI Working Group |
| 18 or 19 November | PI Working Group Meeting in Buenos Aires -- Discussion and Review of Draft Work Plan, Work Plan Sub-team Mind Map, and proposed Work Plan Timeline. Identify Sub-team interest and leaders. | List of questions regarding and proposed changes to Work Plan | PI Working Group |
| 2 December | Review comments and questions from BA and finalize Work Plan. | Finalize Draft Work Plan | PIWG Work Plan Sub-team (Last Task) |
| 4 December |  |  |  |
| 19 December |  |  |  |
| 2 January 14 |  |  |  |
| 16 January |  |  |  |
| 30 January |  |  |  |
| 13 February |  |  |  |
| 27 February |  |  |  |
| 13 March |  |  |  |
| 24-25 March | PI Working Group Meeting in Singapore – Session presenting Draft Principles to Community | Draft Principles Underpinning GNSO Policy and Implementation Discussions; Proposed Work Plan and Sub-team Formation |  |
| 10 April |  |  |  |
| 24 April |  |  |  |
| 8 May |  |  |  |
| 22 May |  |  |  |
| 5 June |  |  |  |
| 19 June |  |  |  |
| 23-24 June | PI Working Group Meeting in London – Present Final Principles Report and Status Reports on Sub-teams to ACs, SOs and constituencies | Final Draft of Principles (pre or post Public Comments?) Status Reports on Deliverable I and Deliverables II-IV sub-teams |  |
| November | PI Working Group Meeting in ---- Present Draft Process and Framework. | Draft Deliverable I “Process for Development of gTLD policy” and Deliverables II-IV “Framework for Implementation Discussions – Criteria for Determining Policy Process or Implementation – Guidance on IRTs” |  |
| March | PI Working Group Meeting in ---- Presentation of Drafts for Public Comment and discussion at meeting | Final Draft Deliverable I “Process for Development of gTLD policy” and Deliverables II-IV “Framework for Implementation Discussions – Criteria for Determining Policy Process or Implementation – Guidance on IRTs” |  |
| Ju,t | PI Working Group Meeting in ---- |  |  |
| November 2015 | PI Working Group Meeting in ---- | Final Report for Comments and Community Input |  |