## Sheet1
Policy & Implementation Working Group Work Plan |  |  |  | 2013-10-29
|  | Subteam Task | Key Milestones | Completed | May be delayed | Late
Week of | Milestone events | Full Working Group | Work plan Sub-Team | Definitions Sub-Team | Deliverable 0B Sub-Team | Deliverable I Sub-Team | Deliverable II-III Sub-Team | Deliverable IV Sub-Team | Deliverable V Sub-Team
|  |  | Develop Proposed Work Plan for Carrying Out Work Group Charter | Develop working definitions of Terms for use in Work Group | Derive from ICANN charters and materials "working principles" that should underpin GNSO Policy and Implementation-related discussions and determinations | Propose process for developing gTLD and other ICANN policy in the form of GNSO "Policy Development Process" and "Policy Guidance" and propose criteria for determining when each would be appropriate | Develop criteria to be used to determine when a particular action should be addressed by a Policy Development or Guidance process and when it should be considered Implementation and develop framework for discussion of Implementation Options associated with GNSO Policy Recommendations | Draft Guidance on the formation and function of GNSO Implementation Review Teams and their relation to GNSO Policy Recommendations and Implementation programs | Finalize set of principles that underpin any GNSO policy and implementation related discussions, taking into account existing GNSO Operating Procedures, GNSO and ICANN Policy and Implementation Directives, and Community Input
2013-10-28 |  | WG Meeting to plan for BA, review status updates from sub-teams, review SO/AC input received (if any) | Meet to finalize proposed work plan and circulate to WG -- Prepare draft Descriptions of Deliverables | Start deliberations on working definitions - identify which terms need definitions and consider existing / other state of the art terms
2013-11-04 |  |  |  | Continue deliberations on working definitions
2013-11-11 |  | WG Meeting to plan for BA, review status updates from sub-teams, review SO/AC input received | Present Draft Work Plan for Discussion and Revision | Discuss and revise draft Definitions
2013-11-18 | ICANN Meeting in BA | F2F meeting on 20 Nov; discuss & approve Work Plan; discuss & solicit feedback on working definitions | Finalize Work Plan and Draft Timetable | Provide status update on working definitions for discussion and feedback | Sub-team meeting
2013-11-25 |  |  |  | Finalize and Publish Working Definitions to Working Group |  | Call for Volunteers | Call for Volunteers | Call for Volunteers | Call for Volunteers
2013-12-02 |  | WG Meeting - discuss & review (and either approve or set date for final approval) of working definitions |  |  | Sub-team meeting to review tasks as outlined in mind map and determine approach
2013-12-09 |  |  |  |  | Sub-team meeting - begin to discuss working principles
2013-12-16 |  | WG Meeting |  |  | Sub-team meeting
2013-12-23 |  |  |  |  | Sub-team meeting
2013-12-30 |  |  |  |  | Sub-team meeting
2013-01-06 |  | WG Meeting - receive update on "working principles" from 0B |  |  | Sub-team meeting - finalize draft working principles | Contact and Confirm Volunteers | Contact and Confirm Volunteers | Contact and Confirm Volunteers | Contact and Confirm Volunteers
2013-01-13 |  |  |  |  | Sub-team meeting
2013-01-20 |  | WG Meeting -- Review "working principles" from 0B |  |  | Sub-team meeting
2013-01-27 |  |  |  |  | Sub-team meeting | Sub-team meeting to review tasks as outlined in mind map and determine approach | Sub-team meeting to review tasks as outlined in mind map and determine approach | Sub-team meeting to review tasks as outlined in mind map and determine approach
2013-02-03 |  | WG Meeting - Discuss & provide feedback on "working principles"
2013-02-10 |  |  |  |  | Sub-team meeting - revise & finalize "working principles" | Sub-team meeting | Sub-team meeting | Sub-team meeting
2013-02-17 |  | WG Meeting |  |  |  | Sub-team meeting | Sub-team meeting | Sub-team meeting
2013-02-24
2013-03-03 | Publication deadline for ICANN Meeting in Singapore (3 March) | Publish Initial Findings for public comment and/or community consideration (depending on progress made) WG Meeting
2013-03-10 | [5 empty] | Sub-team meeting | Sub-team meeting | Sub-team meeting | Sub-team meeting to review tasks and determine approach
2013-03-17 |  | WG Meeting - review overall Work Plan & progress of sub-teams |  |  |  | Sub-team meeting | Sub-team meeting | Sub-team meeting
2013-03-24 | ICANN Meeting in Singapore | F2F meeting in Singapore & community session |  |  |  | Sub-team meeting | Sub-team meeting | Sub-team meeting
2013-03-31 | [5 empty] | Sub-team meeting | Sub-team meeting | Sub-team meeting
|  |  |  | Sub-team meeting - review public comment received | Sub-team meeting - review public comment received | Sub-team meeting | Sub-team meeting | Sub-team meeting
|  | WG Meeting - review sub-team reports & public comment received |  |  |  | Publish Draft for Public Comment | Publish Draft for Public Comment | . . . | . . .
|  | WG Meeting - discuss public comment; respond/revise Deliverables | [5 empty] | Sub-team meeting to review Deliverables I-III and finalize IV | Sub-team meeting to review deliverables 0B and I-VI
[8 empty] | Sub-team meeting to review Deliverables I-III and finalize IV | Sub-team meeting
[6 empty] | Review Public Comments and Respond/Revise Deliverables | Review Public Comments and Respond/Revise Deliverables | Sub-team meeting to review Deliverables I-III and finalize IV | Sub-team meeting
2013-06-22 | ICANN Meeting in London | WG Meeting -- Review Deliverables I-IV | [5 empty] | Sub-team meeting to review Deliverables I-III and finalize IV
|  | WG Meeting -- Review Deliverables I-IV | [5 empty] | Publish Draft for Public Comment | Sub-team meeting to review deliverables 0B and I-VI
Sub-team meeting to review deliverables 0B and I-VI
Sub-team meeting to review deliverables 0B and I-VI
Sub-team meeting to review deliverables 0B and I-VI
[8 empty] | Sub-team meeting to review public comment received; respond/revise Deliverables | Sub-team meeting to review revised deliverables 0B and I-VI
|  | WG Meeting -- Review Deliverable V and Draft Final Report | [6 empty] | Submit Draft to WG for Review
WG Meeting -- Review Deliverable V and Draft Final Report
2013-10-12 | ICANN Meeting in Los Angeles | WG F2F Meeting in LA; community session
Publish Draft Final Report for Public Comment
|  | Review Public Comment and Revise Final Report | [6 empty] | Review Public Comment and Revise Final Report
Publish Final Report