RAA Subteam B

Proposed Timetable for Completion of Tasks

Ver. 3, 4/23/10

| Date | Topic/Event | Comments |
| --- | --- | --- |
| 4/15/10 | Subteam MEETS: (a) Approve revised timetable (b) Discuss way forward on tasks 2 and 3 (c) Discuss activities in Brussels | Disposition of tasks 2 and 3 to be added into timetable following meeting DONE |
| Week of 4/18/10 | ON LIST: Circulate and discuss proposed revised compilation (Task 1) | DONE 4/23/10 |
| 4/26/10 | Subteam MEETS: (a) Discuss/approve Task 1 compilation; (b) Continue planning for Brussels | Circulate revised task 3 (“next steps”) proposals after meeting ; last call for views on topics to be “flagged” under Task 2 |
| 5/3/10 | Subteam MEETS: (a) Finalize task 1 + 2 compilation; (b) Finalize task 3 recommendations | After meeting, circulate draft of report |
| 5/10/10 | Subteam MEETS: Discuss draft report | Following meeting, circulate revised draft report |
| 5/17/10 | Subteam MEETS: conclude discussion of draft report | Following meeting: circulate text for approval/preparation of separate views, etc. |
| 6/2/10 | Deadline for submission of report | To be advised by staff |
| June 10, 2010 | GNSO Council meets: could take action on report |  |
| June 21, 2010? | “Workshop” on subteam B report at Brussels meeting | Date, format, etc. to be confirmed |
| June 23, 2010 | GNSO Council meets (Brussels): could take action on report |  |