## Matrix
| Recommendation | Sequence | Level of Consenus (RAP working group) |  | Expected Complexity | Expected Scope/stakeholders | Resources required | Nature of effort/approach | Dependencies? | Next Steps
|  | Range 1-16 |  |  | High, medium, low | Broad, medium, narrow | High, medium, low | E.g. Create Working Group, initiate PDP, Drafting Team, send letter | Yes (if so, describe), no | E.g. Request for an Issues Report, call for volunteers
Cybersquatting
1 | The RAPWG recommends the initiation of a Policy Development Process by requesting an Issues Report to investigate the current state of the UDRP, and consider balanced revisions to address cybersquatting if appropriate. This effort should consider: How the UDRP has addressed the problem of cybersquatting to date, and any insufficiencies / inequalities associated with the process; Whether the definition of cybersquatting inherent within the existing UDRP language needs to be reviewed or updated. | 4 | Unanimous Consensus |  | High | Broad | High | Develop Policy (PDP) |  | Request Issue Report
Malicious Use of Domain Names
2 | The RAPWG recommends the creation of non-binding best practices to help registrars and registries address the illicit use of domain names. This effort should be supported by ICANN resources, and should be created via a community process such as a working or advisory group while also taking the need for security and trust into consideration. The effort should consider (but not be limited to) these subjects: Practices for identifying stolen credentials; Practices for identifying and investigating common forms of malicious use (such as malware and phishing); Creating anti-abuse terms of service for inclusion in Registrar-Registrant agreements, and for use by TLD operators; Identifying compromised/hacked domains versus domain registered by abusers; Survey registrars and registries to determine practices being used, and their adoption rate; Security resources of use or interest to registrars and registries; Account access security management; Practices for suspending domain names | 1 | Unanimous Consensus |  | Low | Medium | Low | Drafting team | Yes. Creation of a WG should happen at ICANN Cartagena. This will allow the best practices to be available for registry operators before they launch their new TLDs in 2011 or 2012. Helps address the overarching issue of abuse and security in the nTLDs. | Launch drafting group
Fake Renewal Notices
3 | The RAPWG recommends that the GNSO refer this issue to ICANN’s Contractual Compliance department for possible enforcement action, including investigation of misuse of WHOIS data | 5 | Unanimous Consensus |  | Low | Medium | Low | Implementation | no | Send letter
4 | The following recommendation is conditional. The WG would like to learn the ICANN Compliance Department’s opinions regarding Recommendation #1 above, and the WG will further discuss Recommendation 2 looking forward to the WG’s Final Report. The RAPWG recommends the initiation of a Policy Development Process by requesting an Issues Report to investigate fake renewal notices. | 6 | Unanimous Consensus |  | High | Medium | High | Develop Policy (PDP) | yes -- #3 above -- ask Compliance Department for information. | Request Issue Report
Whois Access
5 | The GNSO should determine what additional research and processes may be needed to ensure that WHOIS data is accessible in an appropriately reliable, enforceable, and consistent fashion. The GNSO Council should consider how such might be related to other WHOIS efforts, such as the upcoming review of WHOIS policy and implementation required by ICANN’s new Affirmation of Commitments. | 2 | Unanimous Consensus |  | Medium | Broad | Low | Drafting team | Suggest that the GNSO Council refer the RAPWG's work on WHOIS Availability to the RAA Drafting Team, which should include WHOIS Accessibility on its list of "high-priority" issues. | Council could issue a Resolution to the RAA Drafting Team
6 | The GNSO should request that the ICANN Compliance Department publish more data about WHOIS accessibility, on at least an annual basis. This data should include a) the number of registrars that show a pattern of unreasonable restriction of access to their port 43 WHOIS servers, and b) the results of an annual compliance audit of compliance with all contractual WHOIS access obligations. | 3 | Unanimous Consensus |  | low | Broad | Low | Implementation | no | Send letter
Cross TLD Registration Scam
7 | The RAPWG recommends the GNSO monitor for Cross-TLD registration scam abuse in the gTLD space and co-ordinate research with the community to determine the nature and extent of the problem. The WG believes this issue warrants review but notes there is not enough data at this time to warrant an Issues Report or PDP. | 7 | Unanimous Consensus | [6 empty] | none
Meta Issue: Uniformity of Reporting
8 | The RAPWG recommends that the GNSO, and the larger ICANN community in general, create and support uniform reporting processes. | Indicate where this project falls in the sequence | Unanimous Consensus | [6 empty] | this is advisory information for GNSO improvements efforts
Meta Issue: Collection and Dissemination of Best Practices
9 | The RAPWG recommends that the GNSO, and the larger ICANN community in general, create and support structured, funded mechanisms for the collection and maintenance of best practices. | Indicate where this project falls in the sequence | Unanimous Consensus | [6 empty] | this is advisory information for GNSO improvements efforts, and follow-up for future Consensus Policies
Uniformity of Contacts
10 | View A: The RAPWG recommends the creation of an Issues Report to evaluate whether a minimum baseline of registration abuse provisions should be created for all in-scope ICANN agreements, and if created, how such language would be structured to address the most common forms of registration abuse. View B: Opposed to the recommendation for an Issues Report as expressed in view A | Indicate where this project falls in the sequence | Strong Support but Significant Opposition |  | High | Broad | High | Develop Policy (PDP) | Yes. This contemplates changes to existing and forthcoming registrar and registry agreements. The NewTLD registry contract will be finalized late 2010, and the RAA Drafting Team is already far along. May complicate those efforts or open up old issues again. | Request Issue Report
Cybersquatting
11 | View A: The RAPWG recommends the initiation of a Policy Development Process by requesting an Issues Report to investigate the appropriateness and effectiveness of how any Rights Protection Mechanisms that are developed elsewhere in the community (e.g. the New gTLD program) can be applied to the problem of cybersquatting in the current gTLD space. View B: The initiation of such a process is premature; the effectiveness and consequences of the Rights Protection Mechanisms proposed for the new TLDs is unknown. Discussion of RPMs should continue via the New TLD program. Experience with them should be gained before considering their appropriate relation (if any) to the existing TLD space. | Indicate where this project falls in the sequence | Split opinion |  | High | Broad | High | Develop Policy (PDP) | Yes. Results / effectiveness of the New TLD RPMs will not be measurable until at least the year 2013. | Request Issue Report
GRIPE SITES; DECEPTIVE and/or OFFENSIVE DOMAIN NAMES
12 | Make no recommendation. The majority of RAPWG members expressed that gripe site and offensive domain names that use trademarks should be addressed in the context of cybersquatting and the UDRP for purposes of establishing consistent registration abuse policies in this area, and that creating special procedures for special classes of domains, such as offensive domain names, may present problems. | Indicate where this project falls in the sequence | Rough Consensus | [6 empty] | N/A: RAPWG recommended no action.
13 | The URDP should be revisited to determine what substantive policy changes, if any, would be necessary to address any inconsistencies relating to decisions on “gripe” names and to provide for fast track substantive and procedural mechanisms in the event of the registration of deceptive domain names that mislead adults or children to objectionable sites. | Indicate where this project falls in the sequence | Alternate view | [6 empty] | N/A: RAPWG recommended no action.
14 | View A: Turn down a proposed recommendation that registries develop best practices to restrict the registration of offensive strings. View B: Registries should consider developing internal best practice policies that would restrict the registration of offensive strings in order to mitigate the potential harm to consumers and children. | Indicate where this project falls in the sequence | Strong Support, but Significant Opposition | [6 empty] | N/A: RAPWG recommended no action.
Domain Kiting/Tasting
15 | It is unclear to what extent domain kiting happens, and the RAPWG does not recommend policy development at this time. The RAPWG suggests that the Council monitor the issue (in conjunction with ongoing reviews of domain-tasting), and consider next steps if conditions warrant. | Indicate where this project falls in the sequence | Rough Consensus | [6 empty] | N/A: RAPWG recommended no action.
16 | The RAPWG recommends policy development regarding domain kiting / tasting with input from the appropriate parties | Indicate where this project falls in the sequence | Alternate view | [6 empty] | N/A: RAPWG recommended no action.
Ignore everything below… it's just stuff for the drop-down menus
|  |  |  | High | High | Broad | High | Advisory group |  | Request Issue Report
|  |  |  | Medium | Medium | Medium | Medium | Drafting team |  | Initiate advisory group
|  |  |  | Low | Low | Narrow | Low | Implementation |  | Send letter
[8 empty] | Technical |  | Request initial report
[8 empty] | Develop Policy (PDP) |  | Launch drafting group
#VALUE!
|  |  | 1 | 1
|  |  | 2 | 2
|  |  | 3 | 3
|  |  | 4 | 4
|  |  | 5 | 5
|  |  | 6 | 6
|  |  | 7 | 7
|  |  | 8 | 8
|  |  | 9 | 9
|  |  | 10 | 10
|  |  | 11 | 11
|  |  | 12 | 12
|  |  | 13 | 13
|  |  | 14 | 14
|  |  | 15 | 15
|  |  | 16 | 16

## Admin
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6 | 6
7 | 7
8 | 8
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
15 | 15
16 | 16
#VALUE!