Draft Locking of a Domain Name Subject to UDRP Proceedings WG Work Plan & Timeline

Required Elements to be included:

- Request public input on the issue in order to have a clear understanding of the exact nature and scope of issues encountered with the locking of a domain name subject to UDRP Proceedings (e.g. public comment forum, expert testimony, workshop in Prague, survey?)

- Request for Stakeholder Group / Constituency Statements (minimum of 35 days)

- Formally seek the opinion of other ICANN Advisory Committees and Supporting Organizations early on in the process

- Consideration of charter questions:

  - 1. Whether the creation of an outline of a proposed procedure, which a complainant must follow in order for a registrar to place a domain name on registrar lock, would be desirable.

  - 2. Whether the creation of an outline of the steps of the process that a registrar can reasonably expect to take place during a UDRP dispute would be desirable.

  - 3. Whether the time frame by which a registrar must lock a domain after a UDRP has been filed should be standardized.

  - 4a. Whether what constitutes a “locked" domain name should be defined.

  - 4b. Whether, once a domain name is 'locked' pursuant to a UDRP proceeding, the registrant information for that domain name may be changed or modified.

  - 5. Whether additional safeguards should be created for the protection of registrants in cases where the domain name is locked subject to a UDRP proceeding.

- Publication of Initial Report

- Public comment forum on Initial Report (minimum of 30 days)

- Review of public comments received on Initial Report

- Publication of Final Report

| Target Date | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 26 April 2012 | Locking WG Meeting | Chair Election Development of Work Plan Discuss approach to address issue | All |
| 3 May 2012 | Locking WG Meeting |  | All |
| 3 May 2012 | Deadline for session requests for the ICANN Meeting in Prague |  | Staff |
| 10 May 2012 | Locking WG Meeting |  | All |
| 17 May 2012 | Locking WG Meeting |  | All |
| 24 May 2012 | Locking WG Meeting |  | All |
| 31 May 2012 | Locking WG Meeting |  | All |
| 1 June 2012 | Publication deadline for ICANN Meeting in Prague |  |  |
| 7 June 2012 | Locking WG Meeting |  | All |
| 14 June 2012 | Locking WG Meeting |  | All |
| 21 June 2012 | Locking WG Meeting |  | All |
| 23-29 June 2012 | ICANN Meeting in Prague |  |  |
| 28 June 2012 | Locking WG Meeting |  | All |
| 5 July 2012 | Locking WG Meeting |  | All |
| 12 July 2012 | Locking WG Meeting |  | All |
| 19 July 2012 | Locking WG Meeting |  | All |
| 26 July 2012 | Locking WG Meeting |  | All |
| 2 August 2012 | Locking WG Meeting |  | All |
| 9 August 2012 | Locking WG Meeting |  | All |
| 16 August 2012 | Locking WG Meeting |  | All |
| 23 August 2012 | Locking WG Meeting |  | All |
| 30 August 2012 | Locking WG Meeting |  | All |
| 6 September 2012 | Locking WG Meeting |  | All |
| 13 September 2012 | Locking WG Meeting |  | All |
| 20 September 2012 | Locking WG Meeting |  | All |
| 21 September 2012 (TBC) | Publication Deadline for ICANN Meeting in Toronto |  |  |
| 13-19 October 2012 | ICANN Meeting in Toronto |  |  |